## Sheet1
| 3/7/17 | [18 empty] | Contacts |  |  |  | Planning | [7 empty] | Regulatory | [6 empty] | Land
RIG | WELL | Why Scheduled? | WI | STATUS | AREA | TZ | LAT LEN | SHL | BHL | PAD | SPUD-SPUD | SPUD | RIG RELEASE | LAND | MSB | Net Ac @ Risk | MPB | COMPLETION | NOTE | LAND | GEO OPS | DRILLING | COMPL. | SHL | SURVEY REQUEST | RTS | STAKED | PLAT | GEOPROG | DIR PLAN | AFE | NPZ | SWR-37 | W1 | GAU | SWR-13 | WWP | REGUL. RTD | SUA | ACCESS | FACILITIES | SURF RTB | LOC BUILT | MINERAL RTD | FULL RTD | time axis 2017-01-01 to 2018-01-01
HP 650 | Balmorhea State 2H | lease driven | 100% | completing | Arroyo | UA | 7500 |  | Blk C9/Sec. 7-44 | 1-pad | 25 | 2016-12-19 |  | HARD | 2017-01-08 |  |  | 2017-02-21 | Drilling | Taylor | Joe | Aldo | Brandon | on lease | X | x | x | x | x | x | x | x |  | x | x | x | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 650 | Russell 6H | development | 100% | WOC | Toyah | UA | 5000 | B. 13/S. 275 | B. 13/S. 275 | 1-pad | 20 | 2017-01-13 |  | EASY |  |  |  | 2017-03-27 | Drilling | Bradley | Joe | Aldo | Brandon | on lease | x | x | x | x | x | x | 300400 |  |  | x | x | x | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 650 | Compton 2H | development | 100% | drill | Toyah | UA | 5000 | B. 13/S. 277 | B. 13/S. 277 | 2-pad | 20 | 2017-02-09 |  | EASY |  |  |  | 2017-04-23 | U/L 880 development | Bradley | Joe | Aldo | Brandon | on lease | x | x | x | x | x | x | 300467 |  |  | x | x | x | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 650 | Compton 3H | development | 100% | drill | Toyah | LA | 5000 | B. 13/S. 277 | B. 13/S. 277 | 2-pad | 20 | 2017-03-01 |  | EASY |  |  |  | 2017-04-23 | U/L 880 development | Bradley | Joe | Aldo | Brandon | on lease | x | x | x | x | x | x | 300468 |  |  | x | x | x | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 650 | Red Crest 4H |  |  | scheduled | Toyah | C | 5000 | B. 13/S. 248 | B. 13/S. 249 | 1-pad | 20 | 2017-03-21 |  | EASY |  |  |  |  | WC mirror of Blue Crest 2H | Bradley | Joe | Aldo | Brandon | off lease | x | x | x | x | x |  | 300535 |  |  | subm. |  |  |  |  | x | x | x | x | building | x
HP 650 | Carpenter State 3H | lease driven | 100% | scheduled | Toyah | UA | 5000 | B. 13/S. 248 | B. 13/S. 248 | 1-pad | 20 | 2017-04-10 |  | EASY | 2017-05-01 | 40+E2 CDC |  |  | W2 of sec., lease driven | Bradley | Joe | Aldo | Brandon | on lease | x | x | x | x | x |  | 300539 |  |  | w/o Land |  |  |  |  | cont surf own (12) | cont surf own (12) | time axis 2017-01-01 to 2018-01-01
HP 650 | Sundown 1H | southern test |  | scheduled | Big Chief | LA | 5000 | B. 13/S. 300 | B. 13/S. 300 | 1-pad | 20 | 2017-04-30 |  | EASY |  |  |  |  | section 300 north Big Chief east 5K test | Bradley | Joe | Aldo | Brandon | on lease | x | wo perm /access | wo perm /access | time axis 2017-01-01 to 2018-01-01
HP 650 | Adobe A 3H | lease driven | ~80% | scheduled | Toyah | UA | 10000 | B. 13/S. 210 | B. 13/S. 211 | 2-pad | 30 | 2017-05-20 |  | EASY | 4/22/2017 -6/2/17 | 10 & 3 |  |  | U/L 880 development, lease driven | Taylor | Joe | Aldo | Brandon | on lease | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 650 | Adobe B 4H | development | ~80% | scheduled | Toyah | LA | 10000 | B. 13/S. 210 | B. 13/S. 211 | 2-pad | 30 | 2017-06-19 |  | EASY |  |  |  |  | U/L 880 development | Taylor | Joe | Aldo | Brandon | on lease | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 650 | Roadrunner 6H | development | 92% | scheduled | Toyah | LA | 10000 | B. 52 7S/S. 37 | B. 52 7S/S. 48 | 2-pad | 30 | 2017-07-19 |  | EASY |  |  |  |  | U/L 880 development | Taylor | Joe | Aldo | Brandon | on lease | x | time axis 2017-01-01 to 2018-01-01
HP 650 | Roadrunner 7H | development | 92% | scheduled | Toyah | LA | 10000 | B. 52 7S/S. 37 | B. 52 7S/S. 48 | 2-pad | 30 | 2017-08-18 |  | EASY |  |  |  |  | U/L 880 development | Taylor | Joe | Aldo | Brandon | on lease | x | time axis 2017-01-01 to 2018-01-01
HP 650 | War Eagle 1H | southern test |  | scheduled | Big Chief | LA | 10000 | B. 13/S. 295 | B. 13/S. 294 | 1-pad | 30 | 2017-09-17 |  | MED |  |  |  |  | north Big Chief west 10K test | Bradley | Joe | Aldo | Brandon | on lease | x | wo perm /access | wo perm /access | time axis 2017-01-01 to 2018-01-01
HP 650 | Red Crest | development |  | proposing | Toyah | UA | 5000 |  | Blk 13/Sec. 295-294 | 3-pad | 20 | 2017-10-17 | [7 empty] | Bradley | Joe | Aldo | Brandon
HP 650 | Purple Crest | development |  | proposing | Toyah | LA | 10000 |  | Blk 52 7N/Sec. 37-48 | 3-pad | 30 | 2017-11-06 | [7 empty] | Bradley | Joe | Aldo | Brandon
HP 650 | Purple Crest | development |  | proposing | Toyah | UA | 10000 |  | Blk 52 7N/Sec. 37-48 | 3-pad | 30 | 2017-12-06 | [7 empty] | Bradley | Joe | Aldo | Brandon
HP 650 | Barracuda | lease driven |  | proposing | Toyah | UA | 10000 |  |  | 2-pad | 30 | 2018-01-05 |  |  | 2018-03-27 |  |  |  |  | Taylor | Joe | Aldo | Brandon
HP 650 | Barracuda | development |  | proposing | Toyah | LA | 10000 |  |  | 2-pad | 30 | 2018-02-04 | [7 empty] | Taylor | Joe | Aldo | Brandon
HP 650 | Bentz 312 | southern test |  | proposing | Big Chief | LA | 10000 |  |  | 1-pad | 30 | 2018-03-06 | [7 empty] | Bradley | Joe | Aldo | Brandon
HP 650 | [6 empty] | 10000 |  |  |  | 30 | 2018-04-05 | time axis 2017-01-01 to 2018-01-01
HP 618 | Collins 2H | development | 90% | WOC | Toyah | UA | 7500 | B. 52 7S/S. 24 | B. 52 7S/S. 25 | 1-pad | 25 | 2017-01-07 |  | EASY |  |  |  | 2017-03-13 | drilling | Taylor | Liam | Brett | Brandon | on lease | x | x | x | x | x | x | 300411 |  |  | x | x | x | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 618 | Shelby State 2H | development | 100% | drill | Toyah | UA | 5000 | B. 52 7S/S. 37 | B. 13/S. 280 | 2-pad | 20 | 2017-02-01 |  | EASY |  |  |  | 2017-04-12 | U/L 880 development, CDC driven | Taylor | Liam | Braden | Brandon | off lease | x | x | x | x | x | x | 300462 |  |  | x | x | n/a | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 618 | Shelby State 3H | development | 100% | drill | Toyah | LA | 5000 | B. 52 7S/S. 37 | B. 13/S. 280 | 2-pad | 20 | 2017-02-21 |  | EASY |  |  |  | 2017-04-12 | U/L 880 development, CDC driven | Taylor | Liam | Braden | Brandon | off lease | x | x | x | x | x | x | 300463 |  |  | x | x | n/a | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 618 | Roadrunner 5H | development | 92% | scheduled | Toyah | UA | 10000 | B. 52 7S/S. 48 | B. 52 7S/S. 37 | 1-pad | 30 | 2017-03-13 |  | EASY |  |  |  |  | eastern section line WA development location | Taylor | Liam | Braden | Brandon | on lease | x | x | x | x | x |  | 300531 |  |  | subm |  |  |  |  | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 618 | Balmorhea State B 3H | lease driven-CDC |  | scheduled | Arroyo | LA | 7500 | B. C9/S. 7 | B. 6/S. 44 | 2-pad | 25 | 2017-04-12 |  | EASY | 2017-05-01 |  |  |  | U/L 880 development, CDC driven | Taylor | Liam | Braden | Brandon | on lease | x | x | x | x | prelim |  |  |  |  | P-16/Chg Plat | time axis 2017-01-01 to 2018-01-01
HP 618 | Balmorhea State C 4H | development |  | scheduled | Arroyo | UA | 7500 | B. C9/S. 7 | B. 6/S. 44 | 2-pad | 25 | 2017-05-07 |  | EASY |  |  |  |  | U/L 880 development, CDC driven | Taylor | Liam | Braden | Brandon | on lease | x | x | x | x | prelim |  |  |  |  | P-16/Chg Plat | time axis 2017-01-01 to 2018-01-01
HP 618 | Johnson State 3H | lease driven |  | scheduled | Arroyo West | UA | 10000 | B. C9/S. 1 | B. C10/S. 26 | 3-pad | 30 | 2017-06-01 |  | EASY |  |  |  |  | U/L 880 development | Taylor | Liam | Braden | Brandon | on lease | wo geo | time axis 2017-01-01 to 2018-01-01
HP 618 | Johnson State 4H | development |  | scheduled | Arroyo West | UA | 10000 | B. C9/S. 1 | B. C10/S. 26 | 3-pad | 30 | 2017-07-01 |  | EASY |  |  |  |  | U/L 880 development | Taylor | Liam | Braden | Brandon | on lease | wo geo | time axis 2017-01-01 to 2018-01-01
HP 618 | Balmorhea State D 5H | lease driven-CDC |  | scheduled | Arroyo | LA | 7500 | B. C9/S. 7 | B. 6/S. 44 | 2-pad | 25 | 2017-07-31 |  | MED | CDC |  |  |  | lease driven (1/18?) | Taylor | Liam | Braden | Brandon | off lease | wo NBL | time axis 2017-01-01 to 2018-01-01
HP 618 | Balmorhea State E 6H | development |  | scheduled | Arroyo | UA | 7500 | B. C9/S. 7 | B. 6/S. 44 | 2-pad | 25 | 2017-08-25 | [7 empty] | Taylor | Liam | Braden | Brandon | off lease | wo NBL | time axis 2017-01-01 to 2018-01-01
HP 618 | CH Knight | "C" test |  | proposing | Arroyo | C | 5000 | B. 6/S. 31 | B. 6/S. 31 | 1-pad | 20 | 2017-09-19 |  | MED |  |  |  |  | lease driven (1/18?) | Aaron | Liam | Braden | Brandon | time axis 2017-01-01 to 2018-01-01
HP 618 | Prewitt 1H | lease driven |  | proposing | Arroyo | UA | 7500 |  |  | 1-pad | 25 | 2017-10-09 |  |  | 2018-01-01 |  |  |  |  | Taylor | Liam | Brett | Brandon
HP 618 | CWI State Long | lease driven |  | proposing | Arroyo | UA | 10000 |  |  | 3-pad | 30 | 2017-11-03 |  |  | 2018-02-01 | 160 |  |  |  | Aaron | Liam | Brett | Brandon
HP 618 | CWI State Long | development |  | proposing | Arroyo | LA | 10000 |  |  | 3-pad | 30 | 2017-12-03 | [7 empty] | Aaron | Liam | Brett | Brandon
HP 618 | CWI State Long | development |  | proposing | Arroyo | UA | 10000 |  |  | 3-pad | 30 | 2018-01-02
[7 empty] | 10000 |  |  |  | 30 | 2018-02-01
Trin. 123 | Fellers State Unit 3H | development | 70% | WOC | Arroyo | UA | 5000 | B. 50 7S/S. 16 | B. 50 7S/S. 16 | 2-pad | 25 | 2016-12-25 |  | EASY |  |  |  | 2017-03-21 | U/L 880 development | Aaron | Liam | Aldo | Daniel | on lease | x | x | x | x | x | x | 300431 |  |  | x | x | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
Trin. 123 | Fellers State Unit 4H | development | 70% | WOC | Arroyo | UA | 5000 | B. 50 7S/S. 16 | B. 50 7S/S. 16 | 2-pad | 25 | 2017-01-19 |  | EASY |  |  |  | 2017-03-21 | U/L 880 development | Aaron | Liam | Aldo | Daniel | on lease | x | x | x | x | x | x | 300433 |  |  | x | x | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
Trin. 123 | Blackstone 2H | development | 52% | drill | Arroyo | LA | 5000 | B. 50 7S/S. 18 | B. 50 7S/S. 18 | 2-pad | 20 | 2017-02-13 |  | EASY |  |  |  | 2017-05-15 | U/L 880 development | Aaron | Liam | Aldo | Daniel | on lease | x | x | x | x | x | x | 300268 | subm |  | x | x | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
Trin. 123 | Blackstone 1H | development | 52% | drill | Arroyo | UA | 5000 | B. 50 7S/S. 18 | B. 50 7S/S. 18 | 2-pad | 20 | 2017-03-05 |  | EASY |  |  |  |  | U/L 880 development | Aaron | Liam | Aldo | Daniel | on lease | x | x | x | x | x | x | 300267 | subm |  | x | x | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
Trin. 123 | Hightower State Unit 2H | lease driven | 100% | scheduled | Arroyo | UA | 10000 | B. 51 7S/S. 48 | B. 51 8S/S. 1 | 1-pad | 30 | 2017-03-25 |  | EASY |  |  |  |  | single loc. to delineate and HBP | Aaron | Liam | Aldo | Daniel | on lease | x | x | x | x | prelim |  | 300491 |  |  | x | x | ? |  |  | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
Trin. 123 | Fellers State Unit 5H | development | 70% | scheduled | Arroyo | UA | 5000 | B. 50 7S/S. 16 | B. 50 7S/S. 16 | 3-pad | 20 | 2017-04-24 |  | EASY |  |  |  |  | U/L/U 880 development | Aaron | Liam | Aldo | Daniel | on lease | x | x | x | x | next |  |  |  |  | x | x | w/o data | [5 empty] | x | time axis 2017-01-01 to 2018-01-01
Trin. 123 | Fellers State Unit 6H | development | 70% | scheduled | Arroyo | LA | 5000 | B. 50 7S/S. 16 | B. 50 7S/S. 16 | 3-pad | 20 | 2017-05-14 |  | EASY |  |  |  |  | U/L/U 880 development | Aaron | Liam | Aldo | Daniel | on lease | x | x | x | x | next |  |  |  |  | x | x | w/o data | [5 empty] | x | time axis 2017-01-01 to 2018-01-01
Trin. 123 | Fellers State Unit 7H | development | 70% | scheduled | Arroyo | UA | 5000 | B. 50 7S/S. 16 | B. 50 7S/S. 16 | 3-pad | 20 | 2017-06-03 |  | EASY |  |  |  |  | U/L/U 880 development | Aaron | Liam | Aldo | Daniel | on lease | x | x | x | x | next |  |  |  |  | x | x | w/o data | [5 empty] | x | time axis 2017-01-01 to 2018-01-01
Trin. 123 | Cabrito State 7H | development | 100% | scheduled | Arroyo | LA | 5000 | B. 6/S. 26 | B. 6/S. 26 | 3-pad | 20 | 2017-06-23 | [7 empty] | Aaron | Liam | Aldo | Daniel | on lease | x-scouted |  | sched | time axis 2017-01-01 to 2018-01-01
Trin. 123 | Cabrito State 8H | development | 100% | scheduled | Arroyo | UA | 5000 | B. 6/S. 26 | B. 6/S. 26 | 3-pad | 20 | 2017-07-13 | [7 empty] | Aaron | Liam | Aldo | Daniel | on lease | x-scouted |  | sched | time axis 2017-01-01 to 2018-01-01
Trin. 123 | Cabrito State 9H | development | 100% | scheduled | Arroyo | LA | 5000 | B. 6/S. 26 | B. 6/S. 26 | 3-pad | 20 | 2017-08-02 | [7 empty] | Aaron | Liam | Aldo | Daniel | on lease | x-scouted |  | sched | time axis 2017-01-01 to 2018-01-01
Trin. 123 | Blackstone 3H | 80-ac spacing test | 50% | scheduled | Arroyo | UA | 5000 | B. 50 7S/S. 18 | B. 50 7S/S. 18 | 3-pad | 20 | 2017-08-22 |  |  | 2017-12-02 | 160 |  |  |  | Aaron | Liam | Aldo | Daniel | on lease | x | x | x | x
Trin. 123 | Blackstone 4H | 80-ac spacing test | 50% | scheduled | Arroyo | UA | 5000 | B. 50 7S/S. 18 | B. 50 7S/S. 18 | 3-pad | 20 | 2017-09-11 | [7 empty] | Aaron | Liam | Aldo | Daniel | on lease | modify existing
Trin. 123 | Blackstone 5H | 80-ac spacing test | 50% | scheduled | Arroyo | UA | 5000 | B. 50 7S/S. 18 | B. 50 7S/S. 18 | 3-pad | 20 | 2017-10-01 | [7 empty] | Aaron | Liam | Aldo | Daniel | on lease | new
Trin. 123 | CH Knight | "B" test |  | proposing | Arroyo | B | 5000 |  |  | 1-pad | 20 | 2017-10-21 | [7 empty] | Aaron | Liam | Aldo | Daniel
Trin. 123 | Sieber Trust | development |  | proposing | Arroyo | LA | 10000 |  |  | 3-pad | 30 | 2017-11-10 | [7 empty] | Aaron | Liam | Aldo | Daniel
Trin. 123 | Sieber Trust | development |  | proposing | Arroyo | UA | 10000 |  |  | 3-pad | 30 | 2017-12-10 | [7 empty] | Aaron | Liam | Aldo | Daniel
Trin. 123 | Sieber Trust | development |  | proposing | Arroyo | LA | 10000 |  |  | 3-pad | 30 | 2018-01-09
[7 empty] | 10000 |  |  |  | 30 | 2018-02-08 | time axis 2017-01-01 to 2018-01-01
RIG | WELL | Why Scheduled? | WI | STATUS | AREA | TZ | LAT LEN | SHL BLK | SHL SEC | PAD | SPUD-SPUD | SPUD | RIG RELEASE | LAND | MSB | Net Ac @ Risk | MPB | COMPLETION | NOTE | LAND | GEO OPS | DRILLING | COMPL. | SHL | SURVEY REQUEST | RTS | STAKED | PLAT | GEOPROG | DIR PLAN | AFE | NPZ | SWR-37 | W1 | GAU | SWR-13 | WWP | REGUL. RTD | SUA | ACCESS | FACILITIES | SURF RTB | LOC BUILT | MINERAL RTD | FULL RTD | time axis 2017-01-01 to 2018-01-01
Nomac 88 | Ninja 4-50 49 1H | lease driven |  | completing | Arroyo West | UA | 10000 | B. 4/S. 50 | B. 4/S. 49 | 1-pad | 36 | 2016-12-09 |  | EASY |  |  |  | 2017-03-03 | Drilling | Skylar | Joe | Braden | Daniel | on lease | x | x | x | x | x | x | 300460 |  |  | x | x |  |  | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
Nomac 88 | Nicholas 2H | lease driven |  | WOC | Arroyo West | UA | 5000 | B. 5/S. 41 | B. 5/S. 41 | 1-pad | 20 | 2017-01-16 | 2017-02-05 | EASY |  |  |  | 2017-03-13 | Bullpen location | Taylor | Joe | Braden | Daniel | on lease | x | x | x | x | x | x | 300459 |  |  | x | x | n/a | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
Nomac 88 | Samurai 4-49 50 1H | lease driven |  | drill | Arroyo West | UA | 10000 | B. 4/S. 49 | B. 4/S. 50 | 1-pad | 30 | 2017-02-09 |  | MED | 2017-02-11 | 480 |  | 2017-03-30 | lease driven, medium land effort, ops across 2/11 | Skylar | Joe | Braden | Daniel | on lease | x | x | x | x | x |  | 300486 | x | subm (3/16/17) | x | x | n/a | n/a | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
Nomac 88 | Stephens 2H |  |  | scheduled | Arroyo West | UA | 5000 | B. 5/S. 44 | B. 5/S. 44 | 1-pad | 20 | 2017-03-11 |  | EASY |  |  |  |  | east lease line UA, mirror Dynamite Dan 37 1H | Taylor | Joe | Braden |  | on lease | X | x | x | x | x |  | 300528 |  |  | x | x | n/a | subm |  | x | x | x | x | x | x
Nomac 88 | Rifleman C19-3 1H | lease driven |  | scheduled | Arroyo West | UA | 5000 | B. C19/S. 3 | B. C19/S. 3 | 1-pad | 20 | 2017-03-31 |  | HARD | 2017-07-23 | 240 |  |  | lease driven, high land effort | Skylar | Joe | Braden | Daniel | on lease | x | x | x | x | x |  | 300493 |  |  | x | x | ? |  |  | 3 land own | CVX/2 land own |  | pronto | 4-day | time axis 2017-01-01 to 2018-01-01
Nomac 88 | Little Fundamental 4-52 1H | lease driven |  | scheduled | Arroyo West | B | 5000 | B. 4/S. 52 | B. 4/S. 52 | 1-pad | 20 | 2017-04-20 |  | MED | 2017-05-22 | 24 |  |  | lease driven, medium land effort | Skylar | Joe | Braden | Daniel | on lease | x | x | x | drafting own | x |  |  |  |  | w/o Land & Plats | time axis 2017-01-01 to 2018-01-01
Nomac 88 | Big House 4 57-60 1H | lease driven |  | scheduled | Grisham | UA | 7500 | B. 4/S. 60 | B. 4/S. 57 | 2-pad | 25 | 2017-05-10 |  | MED | 2017-07-22 | 160 |  |  | lease driven, high land effort, EXL trade, define unit | Skylar | Joe | Braden | Daniel | on lease | x | wo perm | plan for 3/8 | time axis 2017-01-01 to 2018-01-01
Nomac 88 | Big House 4 57-60 2H | development |  | scheduled | Grisham | UA | 7500 | B. 4/S. 60 | B. 4/S. 57 | 2-pad | 25 | 2017-06-04 |  | MED |  |  |  |  | Pop pair | Skylar | Joe | Braden | Daniel | on lease | x | wo perm | plan for 3/8 | time axis 2017-01-01 to 2018-01-01
Nomac 88 | Pistol C18-24 1H | lease driven |  | proposing | Arroyo West | UA | 5000 | B. C18/S. 24 | B. C18/S. 24 | 1-pad | 20 | 2017-06-29 |  |  | 2017-07-24 | 195 |  |  |  | Skylar | Joe | Braden | Daniel | on lease | x | wo perm /access | wo perm /access | time axis 2017-01-01 to 2018-01-01
Nomac 88 | Powder Keg 4 64-61 1H | lease driven |  | proposing | Grisham | UA | 7500 | B. 4/S. 64 | B. 4/S. 61 | 2-pad | 25 | 2017-07-19 |  |  | 6/1/2017 10/21/17 | 40 (ext) +48 |  |  |  | Skylar | Joe | Braden | Daniel | on lease | wo geo | time axis 2017-01-01 to 2018-01-01
Nomac 88 | Powder Keg 4 64-61 2H | lease driven |  | proposing | Grisham | UA | 7500 | B. 4/S. 64 | B. 4/S. 61 | 2-pad | 25 | 2017-08-13 |  |  | 6/1/2017 10/21/17 | 40 (ext) +48 |  |  |  | Skylar | Joe | Braden | Daniel | on lease | wo geo | time axis 2017-01-01 to 2018-01-01
Nomac 88 | Pop 4 59-60 2H | lease driven |  | proposing | Grisham | LA | 10000 | B. 4/S. 59 | B. 4/S. 60 |  | 30 | 2017-09-07 |  | MED | dev. |  |  |  | MDC AMI - drop | Skylar | Joe | Braden | Daniel | on lease | wo geo
Nomac 88 | Pop 4 59-60 3H | development |  | proposing | Grisham | UA | 10000 | B. 4/S. 59 | B. 4/S. 60 |  | 30 | 2017-10-07 |  | MED | dev. |  |  |  | U/L 880 development | Skylar | Joe | Braden | Daniel | on lease | wo geo | time axis 2017-01-01 to 2018-01-01
Nomac 88 | Ninja 4 50-49 2H | development |  | proposing | Grisham | LA | 7500 | B. 4/S. 49 | B. 4/S.50 | 2-pad | 25 | 2017-11-06 |  | EASY | dev. |  |  |  | U/L 880 development | Skylar | Joe | Braden | Daniel | on lease | time axis 2017-01-01 to 2018-01-01
Nomac 88 | Ninja 4 50-49 3H | development |  | proposing | Grisham | UA | 7500 | B. 4/S. 49 | B. 4/S.50 | 2-pad | 25 | 2017-12-01 |  | EASY | dev. |  |  |  | U/L 880 development | Skylar | Joe | Braden | Daniel | on lease | time axis 2017-01-01 to 2018-01-01
[7 empty] | 10000 |  |  |  | 30 | 2017-12-26
HP 489 | Doc Gardner 3H | development | 99% | drill | Arroyo West | LA | 5000 | B. 13/S. 194 | B. 13/S. 194 | 2-pad | 20 | 2017-02-19 |  | EASY | 2019-01-01 |  |  | 2017-05-04 | U/L 880 development | Taylor | Joe | Ty | Brandon | on lease | X | x | x | x | X | x | 300464 |  |  | x | x | x | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 489 | Doc Gardner 2H | development | 99% | drill | Arroyo West | UA | 5000 | B. 13/S. 194 | B. 13/S. 194 | 2-pad | 20 | 2017-03-11 |  | EASY | 2019-01-01 |  |  | 2017-05-04 | U/L 880 development | Taylor | Joe | Ty | Brandon | on lease | X | x | x | x | X | x | 300465 |  |  | x | x | x | x | x | x | x | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 489 | Brooks 3H | development | 100% | scheduled | Toyah | LA | 10000 | B. 13/S. 277 | B. 13/S. 278 | 2-pad | 30 | 2017-03-31 |  | EASY |  |  |  |  | U/L 880 development | Bradley | Joe | Ty | Brandon | on lease | X | x | x | x | x |  |  |  |  | x | subm |  |  |  | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 489 | Brooks 4H | development | 100% | scheduled | Toyah | UA | 10000 | B. 13/S. 277 | B. 13/S. 278 | 2-pad | 30 | 2017-04-30 |  | EASY |  |  |  |  | U/L 880 development | Bradley | Joe | Ty | Brandon | on lease | X | x | x | x | x |  |  |  |  | x | subm |  |  |  | x | x | x | x | x | time axis 2017-01-01 to 2018-01-01
HP 489 | Parker A Unit 2H | lease driven | 100% | scheduled | Arroyo West | UA | 10000 | B. 5/S. 43 | B. C9/S. 12 | 2-pad | 30 | 2017-05-30 |  | MED | 2017-06-28 | 480? |  |  | MDC AMI - drop | Taylor | Joe | Ty | Brandon | on lease | x | wo perm | stake week 3/6
HP 489 | Parker B Unit 3H | lease driven | 100% | scheduled | Arroyo West | UA | 10000 | B. 5/S. 43 | B. C9/S. 12 | 2-pad | 30 | 2017-06-29 |  | MED | CDC |  |  |  | MDC AMI - drop | Taylor | Joe | Ty | Brandon | on lease | x | wo perm | stake week 3/6
HP 489 | CWI State 9H | development | 50% | scheduled | Arroyo | LA | 5000 | B. 6/S. 34 | B. 6/S. 34 | 3-pad | 20 | 2017-07-29 |  | MED |  |  |  |  | U/L 880 development | Aaron | Joe | Ty | Brandon |  | wo geo | time axis 2017-01-01 to 2018-01-01
HP 489 | CWI State 10H | development | 50% | scheduled | Arroyo | LA | 5000 | B. 6/S. 34 | B. 6/S. 34 | 3-pad | 20 | 2017-08-18 |  | MED |  |  |  |  | U/L 880 development | Aaron | Joe | Ty | Brandon |  | wo geo | time axis 2017-01-01 to 2018-01-01
HP 489 | CWI State 11H | development | 50% | scheduled | Arroyo | UA | 5000 | B. 6/S. 34 | B. 6/S. 34 | 3-pad | 20 | 2017-09-07 | [7 empty] | Aaron | Joe | Ty | Brandon |  | wo geo | time axis 2017-01-01 to 2018-01-01
HP 489 | Charger State | development |  | proposing | Toyah | LA | 5000 |  |  | 3-pad | 20 | 2017-09-27 | [7 empty] | Taylor | Joe | Brett | Daniel | time axis 2017-01-01 to 2018-01-01
HP 489 | Charger State | development |  | proposing | Toyah | UA | 5000 |  |  | 3-pad | 20 | 2017-10-17 | [7 empty] | Taylor | Joe | Brett | Daniel
HP 489 | Charger State | development |  | proposing | Toyah | LA | 5000 |  |  | 3-pad | 20 | 2017-11-06 | [7 empty] | Taylor | Joe | Brett | Daniel | time axis 2017-01-01 to 2018-01-01
HP 489 | Crisan | development |  | proposing | Toyah | UA | 10000 |  |  | 2-pad | 30 | 2017-11-26 | [7 empty] | Taylor | Joe | Brett | Daniel
HP 489 | Crisan | development |  | proposing | Toyah | LA | 10000 |  |  | 2-pad | 30 | 2017-12-26 | [7 empty] | Taylor | Joe | Brett | Daniel
HP 489 | Balmorhea State | lease driven-CDC |  | proposing | Arroyo | LA | 7500 |  |  | 2-pad | 25 | 2018-01-25 | [7 empty] | Taylor | Joe | Brett | Daniel
HP 489 | Balmorhea State | development |  | proposing | Arroyo | UA | 7500 |  |  | 2-pad | 25 | 2018-02-19 | [7 empty] | Taylor | Joe | Brett | Daniel
HP 489 | [6 empty] | 7500 |  |  |  | 25 | 2018-03-16 | time axis 2017-01-01 to 2018-01-01
bullpen | CH Knight 6H |  | 95% | bullpen | Arroyo | UA | 5000 | B. 6/S. 31 | B. 6/s. 31 | 1-pad | 20 | bullpen |  | EASY |  |  |  |  | west lease line UA, mirror CWI 7H | Aaron |  | Brett |  | on lease | x | x | x | x | next | [14 empty] | x
bullpen | Matador 6-33 3H |  | 63% | bullpen | Arroyo | UA | 5000 | B. 6/S. 33 | B. 6/S. 33 | 1-pad | 20 | bullpen |  | EASY |  |  |  |  | pair, UA development loc., straddle 2H | Aaron |  | Brett |  | on lease | x | x | x | drafting lse | next
sched |  |  |  |  | Arroyo West |  | 5000 |  |  |  | 20 | bullpen |  | HARD | 2017-02-25 | 20? |  |  | land challenges, will schedule in when ready | Skylar | Joe | Brett |  |  | x | x |  | x
bullpen | Toyah 47 1H |  |  | add | Toyah | UA | 5000 |  |  |  | 20 | bullpen |  | HARD | 2017-03-27 | 46 |  |  | CXO trade, extending exp ac, time to tie up unleased ac, push until Q4, revisit in Q3 as 10K | Taylor | Joe | Brett |  | ? | x | x
7 | CWI State 11H |  | 50% | 5 | Arroyo |  | 5000 |  |  |  | 20 | bullpen |  | EASY |  |  |  |  | pair, LA development loc., straddle 8H, stagger infill test, 10Ks? | Aaron
8 | CWI State 12H |  | 50% | 5 | Arroyo |  | 5000 |  |  |  | 20 | bullpen |  | EASY |  |  |  |  | pair, LA development loc., straddle 8H, stagger infill test, 10Ks? | Aaron
9 | Crisan 9H |  |  | 7 | Toyah |  | 5000 |  |  |  | 20 | bullpen |  | EASY |  |  |  |  | UA dev. loc., mirror of Adobe 1H | Taylor
10 | Adobe 8H |  |  | 8 | Toyah |  | 5000 |  |  |  | 20 | bullpen |  | EASY |  |  |  |  | LA development loc., mirror Crisan 2H | Taylor
11 | Jaguar 2H |  |  | 9 | Toyah |  | 5000 |  |  |  | 20 | bullpen |  | EASY |  |  |  |  | UA dev. loc., west lease line | Taylor
13 | Bentz 312 3H |  |  | eval | Big Chief |  | 5000 |  |  |  | 20 | bullpen |  | EASY |  |  |  |  | LA loc., on west lease line, want 10Ks
14 | SBE block |  |  | eval | Arroyo West |  | 7500 |  |  |  | 25 | bullpen |  | EASY |  |  |  |  | Ninja, Pop, Iceman, Folk Rolwing | Skylar
15 | SBE block |  |  | eval | Arroyo West |  | 7500 |  |  |  | 25 | bullpen |  | EASY |  |  |  |  | Ninja, Pop, Iceman, Folk Rolwing | Skylar
16 | Layden |  |  | eval | Arroyo |  | 7500 |  |  |  | 25 | bullpen |  | EASY |  |  |  |  | west lease line, WA well, U/L pair | Aaron
17 | Layden |  |  | eval | Arroyo |  | 7500 |  |  |  | 25 | bullpen |  | EASY |  |  |  |  | west lease line, WA well, U/L pair | Aaron
20 | Sieber |  |  | eval | Arroyo |  | 10000 |  |  |  | 30 | bullpen |  | EASY |  |  |  |  | U/L development pair | Aaron
21 | Sieber |  |  | eval | Arroyo |  | 10000 |  |  |  | 30 | bullpen |  | EASY |  |  |  |  | U/L development pair | Aaron
bullpen | Full Nelson 4H |  |  | add | Big Chief | LA | 10000 |  |  |  | 30 | bullpen |  | EASY | 2017-05-01 | 47 |  |  | extend 47 ac, plan later in schedule, work our way towards area |  | Joe | Brett
bullpen | Big Chief 57 1H |  |  | on schedule | Big Chief |  | 10000 |  |  |  | 30 | bullpen |  | HARD |  | 209? |  |  | 6-8 months of land lead time, wait for other results |  | Joe | Brett
bullpen | Challenger State 3H |  |  | on schedule | Toyah |  | 10000 |  |  |  | 30 | bullpen |  | EASY |  |  |  |  | U/L 880 development | Taylor | Liam | Brett
bullpen | Challenger State 4H |  |  | on schedule | Toyah |  | 10000 |  |  |  | 30 | bullpen |  | EASY |  |  |  |  | U/L 880 development | Taylor | Liam | Brett
HP 489 | Long Nicholas 1H |  |  | proposing | Arroyo West |  | 10000 | B. 5/S. 41 | B. 5/S. 9 | 2-pad | 30 | bullpen |  | MED |  |  |  |  | U/L 880 development | Taylor | Joe | Brett |  |  | rev. w/ land | time axis 2017-01-01 to 2018-01-01
HP 489 | Long Nicholas 2H |  |  | proposing | Arroyo West |  | 10000 | B. 5/S. 41 | B. 5/S. 9 | 2-pad | 30 | bullpen |  | MED |  |  |  |  | U/L 880 development | Taylor | Joe | Brett |  |  | rev. w/ land | time axis 2017-01-01 to 2018-01-01
Formulas:
SPUD = [SPUD, row above]+[SPUD-SPUD, row above]